## Screens
Atradius Experience UI Screens
Page No | UI Screens | Info | Scope
1 | Login Page | User Authentication and Authorization | Yes
2 | Default Page(after login) | A default page with following layout 1.Header Side Bar 2.Navbar 3.Mini Dashboard 4.SideBar 5.Centr Content ( A place holder for other page) | Yes
Header Side Bar
3 | Settings Page | View Settings content | Yes
| Pop Up Window - Upload Team Picture and change Slogan | 1.Opens desktop window to select an image to upload 2. Change Slogan | Yes
4 | Ranking Page | View Ranking content | Yes
5 | Activities Page | Manage User activities by adimin user
NavBar
|  | 1.Language Selection 2.Activity list with icon notification on outstanding activities 3.Logout | Yes
Side Bar
6 | Risk Page | 1. To set the risk srategy at team level | Yes
7 | Dashboard Page |  | Yes
8 | Company Page |  | Yes
9 | Customer Portfolio Page | View Customer Info Search Customer Sorting Customer Filter Customer Upload Customer | Yes
Market Page
10 | Small Prospect Page | 1. Search Prospect 2. Filter Prospect 3. Make offer | Yes
11 | Big Prospect Page | 1. Search Prospect 2. Filter Prospect 3. Make offer | Yes
| Pop Up Window - Make Offer Page | 1. View Selected Customer information 2. View Buyer Information 3. Enter Acceptence Rate 3. Enter Price info | Yes
12 | Oustanding offer | TBD
Admin page
13 | Round System Dashboard | 1. Separate tab in this page will have Round system dashboard. 2.Admin can set duration for each round, invalidate other user session ,calculation etc.. | Yes
14 | User Mangement Page | 1.Create User 2.Edit User 3.Create Team 4.Assign user to team | No
16 | Teams Page | Admin should View Teams and associated user information | TBD
17 | Challenge Page |  | Yes

## Features
No | Screen | Feature | Category | Sub Task | Details | Owner | Status | Technical details | End Date
1 | User Login | 1. User Authentication and Authorization 2. After Successful login user navigate to default page. 3. Read User Language preferene at cookies level | User Management | Define user model | User model capable of following 1. User belongs to Team 2. User role whether admin or normal user | Raj | complete |  | 2015-11-30
1 | User Login |  | User Management | Create Json file format | Infosys will provide sample json file based on defined data model | Raj | complete |  | 2015-11-27
1 | User Login |  | User Management | Form the list of teams | 1. Manual task of creating the list of teams and associated user id and password, 2. Representing unit from array of units and contact email address. 3. User duplication to be handled manually | Emanuel/Jonathan |  |  | 2015-12-15
1 | User Login |  | User Management | Modify User File | 1. To fulfill the concept of team and user list belongs to that team. 2. At any given point in time user belongs to one team can't be in other team. | Raj | complete | on the Server | 2015-11-27
1 | User Login |  | User Management | User login validation | 1.Invalid user - Display inline error in red text below the button 2.Invalid password - Display inline error in red text below the button | Raj | Inprogress |  | 2015-12-01
2 | Default Page( After Login ) | Default page with following layout 1.Header Side Bar 2.Navbar 3.Mini Dashboard 4.SideBar 5.Center Content ( A place holder for other page) | Default Page | Show other pages content to center content section | 1. Ability to view other pages in center content section | Raj | complete |  | 2015-11-27
2 | Default Page( After Login ) |  | Default Page | Html page design |  | Emanuel/Jonathan |  |  | 2015-11-27
3 | Settings Page | 1. View Settings Content | Team | Setting page design | Html page design | Emanuel/Jonathan | Not needed
3 | Settings Page | 2 .Logged in user should be able to change the password. | User Management | Change user password |  | Raj | complete |  | 2015-11-27
3 | Settings Page | 3. Logged in user should be able to change the team slogan. | Team | Slogan | View/ update Team slogan | Raj | Inprogress |  | 2015-12-01
| Avatar | 1.Opens desktop window to select an image to upload | Team | Html design for upload screen |  | Emanuel/Jonathan | Not needed
| Avatar | 1.Opens desktop window to select an image to upload | Team | Upload screen Implementation | Upload avatar | Raj | Not Started |  | 2015-12-02
4 | Ranking Page | 1. View Ranking content | Team | Rank page design | Html page design | Emanuel/Jonathan | complete | Specification received from client | 2015-11-27
4 | Ranking Page | 2. Calculate Rank | Team | Calculate Team Rank | Logic for Calculate team ranking | Emanuel/Jonathan |  |  | 2015-11-27
4 | Ranking Page |  | Team | Ranking | View Team Ranking | Ranga | Inprogress |  | 2015-12-04
5 | Risk Page | 1. To set the risk srategy at team level | Risk | Html page design | Logic for Risk strategy 1. 5 types of risk 2. Buyer Risk - static. Buyer rating value (0 to 100, with 100 being best rating) 3. Expected loss Ratio - for an industry and segement value at buyer level | Emanuel/Jonathan | complete | Specification received from client | 2015-11-25
5 | Risk Page |  | Risk | Define model |  | Raj | Not Started |  | 2015-12-02
5 | Risk Page |  | Risk | Create new risk strategy |  | Raj | Not Started |  | 2015-12-09
5 | Risk Page |  | Risk | Modify risk strategy |  | Raj | Not Started |  | 2015-12-09
5 | Risk Page |  | Risk | Delete risk strategy |  | Raj | Not Started |  | 2015-12-09
6 | Nav Bar | 1.Language Selection | Internalization |  | Store User Language preferene at cookies level Screen adopt to user language selection | Prjakta | Inprogress |  | 2015-12-04
6 | Nav Bar | 2.Activity list with icon notification on outstanding activities | Team |  | Logic | Emanuel/Jonathan |  |  | 2015-12-04
6 | Nav Bar | 2.Activity list with icon notification on outstanding activities | Team |  |  | Infosys
6 | Nav Bar | 3.Logout | User Management |  |  | Infosys
7 | Dashboard Page | Ability to view Dashboard | Dashboard | Define model |  | Infosys
7 | Dashboard Page |  | Dashboard | Html page design |  | Emanuel/Jonathan |  |  | 2015-12-09
8 | Company Page | Ability to view Company Page | Company | Define model |  | Infosys
8 | Company Page |  | Company | Html page design |  | Emanuel/Jonathan |  |  | 2015-12-04
9 | Customer Portfolio Page | View Customer Info Search Customer Sorting Customer Filter Customer Upload Customer | Customer | Define model |  | Infosys | complete
9 | Customer Portfolio Page |  | Customer | Html page design |  | Emanuel/Jonathan |  |  | 2015-12-02
10 | Market Page | Tab ( Small Prospect Page ) 1. Search Prospect 2. Filter Prospect 3. Make offer 4.View offer 5.View Small Prospect | Small Prospect | Small prospects data | Provide data in Json format | Emanuel/Jonathan |  |  | 2015-12-07
10 | Market Page |  | Small Prospect | Define Customer/ buyer model | manual task | Infosys
10 | Market Page |  | Small Prospect | Html page design for small prospect |  | Emanuel/Jonathan |  |  | 2015-12-07
10 | Market Page | Tab ( Big Prospect Page ) 1. Search Prospect 2. Filter Prospect 3. Make offer 4.View offer 5.View Big Prospect | Big Prospect | Big prospects data | Provide data in Json format | Emanuel/Jonathan |  |  | 2015-12-07
10 | Market Page |  | Big Prospect | Define Customer/ buyer model | manual task | Infosys
10 | Market Page |  | Big Prospect | Html page design for big prospect |  | Emanuel/Jonathan |  |  | 2015-12-07
10 | Market Page | View Outstanding offers | Outstanding Offer | Html page design for outstanding offer |  | Emanuel/Jonathan |  |  | 2015-12-07
10 | Market Page |  | Big Prospect - Make Offer | html design |  | Emanuel/Jonathan |  |  | 2015-12-07
10 | Market Page |  | Big Prospect - Make Offer | ability to give a quote | at an itration level 1. View Selected Customer information 2. View Buyer Information 3. Enter Acceptence Rate 3. Enter Price info | Infosys
10 | Market Page |  | Small Prospect - Make Offer | html design |  | Emanuel/Jonathan |  |  | 2015-12-07
10 | Market Page |  | Small Proscpet - Make Offer | ability to give a quote for multiple small prospects | at an itration level | Infosys
11 | Admin Page | Round System Dashboard 1. Separate tab in this page will have Round system dashboard. 2.Admin can set duration for each round, invalidate other user session ,calculation etc.. 3. View Round information | Admin - Round System | Define model for round system dashboard |  | Infosys
| Admin Page |  | Admin - Round System | html design for Round system dashboard |  | Emanuel/Jonathan |  |  | 2015-12-10
| Admin Page | Teams Page Admin should View Teams and associated user information | Admin - Teams Page | html design for Teams page |  | Emanuel/Jonathan |  |  | 2015-12-10
| Admin Page |  | Admin - Teams Page | Define model for Teams page |  | Raj
| Admin Page | Challenge Page Admin can set challenge at every round of a game. | Admin - Challenge Page | View Teams and Users page |  | Raj | complete |  | 2015-12-01
10 | Admin Page |  |  | update revenue | Admin users should be able to change the Customer revenues
|  |  | Policy | accept quotation | rule based calculation to select teams |  |  | does the offer list need to be converted to xls
|  |  | Policy | Create Policy File | policy is at iteration level |  |  | use db import from a csv file?
|  |  | Policy | View Policies
|  |  | Policy | View Policy details
|  |  | Policy | accrue premiums | automatically accrue premiums (frequency - once in a round)
|  |  | Policy | create claims | calculation logic? (frequency - once in a round) |  |  | when to introduce claims?
|  |  | Activities | Form the activities model | define the model and the set of actvities
|  |  | Activities | upload activities | manual
|  |  | Activities | view activities | screen to view
|  |  | Activities | mark activities as completed | system to update the status
|  |  | Reporting | number of people
collaboration
country specific participation
effort spent by user/ team
out of office hrs spent

## Data Structures
Record |  |  |  |  | Field | Field Type | Description
Team
[5 empty] | Team name | Text (50 char) | can be changed
[5 empty] | Representing unit | Text (50 char) | uploaded initially. Cannot be changed
[5 empty] | slogan | Text (100 char) | can be changed
[5 empty] | Picture | picture | Team picture
[5 empty] | Team Country | Text (2 char) | set initially
[5 empty] | Capital | Amount | set initially
[5 empty] | Premium | Amount | all the premiums due (for the round)
[5 empty] | Claims | Amount | total value of all open claims (for that round)
[5 empty] | Claims Ratio | Number (1to 100) | calcualted field. History for each round to be kept
[5 empty] | Profit | Amount
[5 empty] | Investment | Amount
[5 empty] | Experience score | Number (1to 100) | calculated value?
[5 empty] | Salesforce size | Amount | value in EUR
[5 empty] | Underwriter department size | Amount | value in EUR
[5 empty] | IT maintenance | Amount | value in EUR
[5 empty] | Marketing budget | Amount | value in EUR
[5 empty] | Facilities | Amount | value in EUR
[5 empty] | Total Expense | Amount | Calculated value total expenses, including the Claims
[5 empty] | Ranking position | Number (1to 100)
| Round level information | [5 empty] | array (within team)
[5 empty] | roundNumber | Number (1to 100)
[5 empty] | Capital | Amount | set initially
[5 empty] | Premium | Amount | all the premiums due (for the round)
[5 empty] | Claims | Amount | total value of all open claims (for that round)
[5 empty] | Claims Ratio | Number (1to 100) | calcualted field. History for each round to be kept
[5 empty] | Profit | Amount
[5 empty] | Investment | Amount | ?
[5 empty] | Experience score | Number (1to 100) | calculated value?
[5 empty] | Salesforce size | Amount | value in EUR
[5 empty] | Underwriter department size | Amount | value in EUR
[5 empty] | IT maintenance | Amount | value in EUR
[5 empty] | Marketing budget | Amount | value in EUR
[5 empty] | Facilities | Amount | value in EUR
[5 empty] | Total Expense | Amount | Calculated value total expenses, including the Claims
[5 empty] | Ranking position | Number (1to 100)
| Member | [5 empty] | array (within team)
[5 empty] | Email address | Text (50 char) | email address will be the id to access the system
[5 empty] | Password | Text (20 char)
[5 empty] | Name | Text (50 char) | name of the person (full name). User enterable field
Login information
[5 empty] | Team login information (start time) | DateTime | start and end time for each logged in session for the team
[5 empty] | Team login information (end time) | DateTime | start and end time for each logged in session for the team
[5 empty] | country of login | Text (2 char) | country of login, using location APIs
Risk Strategy
[5 empty] | Round | Number (1 to 100)
[5 empty] | Strategy name | Text (30 char)
[5 empty] | Buyer country | Text (2 char)
[5 empty] | Buyer industry | Text (30 char)
|  | Rating range acceptance |  |  |  | Array
[5 empty] | Buyer rating range from | Number (1to 100)
[5 empty] | Buyer rating range to | Number (1to 100)
[5 empty] | Risk acceptance rate | Number (1to 100)
Offer
[5 empty] | Round | Number (1 to 100)
[5 empty] | Market - Business Name | Text (30 char)
[5 empty] | Premium | Amount | calculated from the % for the round
[5 empty] | Premium % | Number (1 to 100)
[5 empty] | Risk strategy | ID | to link to the risk strategy
[5 empty] | Offer Score | Number
| Customer | [5 empty] | copy of market
[5 empty] | Business name | Text (30 char)
[5 empty] | Business Revenue | Amount
[5 empty] | Business Country | Text (2char)
[5 empty] | Business risk | Number (1 to 100) | calculated field (average risk of the buyers)
[5 empty] | Experience score needed | Number (1 to 100) | a value represents the required experience of the team that is required to offer a quote to the Customer. Values between 0 and 100, 100 being max
[5 empty] | Total Premium | Amount
[5 empty] | Total Claims | Amount
|  |  |  | Buyer Portfolio |  |  | (array within Market)
[5 empty] | Buyer country | Text (2 char)
[5 empty] | Buyer industry | Text (30 char)
[5 empty] | Buyer Rating | Number (1 to 100)
[5 empty] | CLA | Amount | business with the buyer
|  | Agreement |  |  |  |  | copy of offer
[5 empty] | Premium | Amount | calculated from the % for the round
[5 empty] | Premium % | Number (1 to 100)
[5 empty] | Risk strategy ID | ID | links to the risk strategy used
[5 empty] | Status | Text (10 char) | Active/ Closed
Claims
[5 empty] | Claim Number | ID
[5 empty] | Buyer Portfolio | ID | Id to link to the buyer portfolio
[5 empty] | Claim Amount | Amount | in EUR
[5 empty] | Round | Number (1 to 100) | round in which claim is raised
Activity Completion
[5 empty] | Round | Number (1 to 100)
[5 empty] | Actvity Name | Text (30 char) | array of activities
[5 empty] | Weightage for activity | Number (1 to 100) | array of activities
[5 empty] | % Completion | Number (1 to 100) | Calculated field for all the activities for the round and team
| Notifications | [5 empty] | should it be at Team level or user level -----not needed
[5 empty] | Round | Number (1 to 100)
[5 empty] | Notification Header | Text (30 char)
[5 empty] | Notification Text | Text (300 char)
[5 empty] | status | Text (10 char)
[5 empty] | Display Type | Text (10 char) | to indicate whether the notification should be displayed all the time or deleted after showing once
Market
Organization
[5 empty] | Business name | Text (30 char)
[5 empty] | Business Revenue | Amount
[5 empty] | Business Country | Text (2 char)
[5 empty] | Business Sector | Text(30 char)
[5 empty] | Business risk | Number (1 to 100) | calculated field (average risk of the buyers)
[5 empty] | Experience score needed | Number (1 to 100) | a value represents the required experience of the team that is required to offer a quote to the Customer. Values between 0 and 100, 100 being max
|  | Buyer Portfolio |  |  |  |  | (array within Market)
[5 empty] | Buyer country | Text (2 char)
[5 empty] | Buyer industry | Text (30 char)
[5 empty] | tpe | Number (1 to 100)
[5 empty] | Buyer Rating | Number (1 to 100)
[5 empty] | CLA | Amount | business with the buyer
Country
[5 empty] | Country ID | Text (2 char)
[5 empty] | Country Name | Text (30 char)
[5 empty] | GDP | Amount | Total/Continent/Country
[5 empty] | Insolvencies | ? | Country/Industry
Activity
[5 empty] | Round | Number (1 to 100)
[5 empty] | Actvity Name | Text (30 char) | array of activities
[5 empty] | Weightage for activity | Number (1 to 100) | array of activities
Round
[5 empty] | Round ID | Number (1 to 100)
[5 empty] | Round Name | Text (30 char) | name for the round (display this field in the screens)
[5 empty] | Round Start Date | DateTime
[5 empty] | Round End Date | DateTime
[5 empty] | Current Round Flag | Boolean | set to True for the current round
[5 empty] | Calculation Flag | Boolean | flag to indicate calcution is done.

## Sheet1
Atradius Experience UI Screens
Page No | UI Screens | Info | Specification? | Status
1 | Login Page | User Authentication and Authorization | Yes | Complete
2 | Default Page(after login) | A default page with following layout 1.Header Side Bar 2.Navbar 3.Mini Dashboard 4.SideBar 5.Centr Content ( A place holder for other page) | Yes | Complete
Header Side Bar
3 | Settings Page | 1.Opens desktop window to select an image to upload 2. Change Slogan 3.Change password | Yes | Complete
4 | Ranking Page | View Ranking content 1.Overall Ranking 2.Country level Ranking | Yes | Complete
5 | Activities Page | Manage User activities by adimin user | No | Not started
NavBar
|  | 1.Language Selection | Yes | Complete
|  | 2.Activity list with icon notification on outstanding activities | No | Not started
|  | 3.Logout | Yes | Complete
Side Bar
6 | Risk Page | To set the risk srategy at team level | Yes | In progress
7 | Dashboard Page | View Dashboard |  | Not started
8 | Company Page | 1. Projects 2. Departments 3. Financials | Yes | Inprogress
9 | Customer Portfolio Page | View Customer Info Search Customer Sorting Customer Filter Customer Upload Customer | No | Not started
10 | Market Page - Small Prospect Page | 1. Search Prospect 2. Filter Prospect 3. Make offer | No | Not started
11 | Market Page - Big Prospect Page | 1. Search Prospect 2. Filter Prospect 3. Make offer | Yes | In progress
| Market Page -Pop Up Window - Make Offer Page(Big prospect) | 1. View Selected Customer information 2. View Buyer Information 3. Enter Acceptence Rate 3. Enter Price info | Yes | Inprogress
12 | Oustanding offer | TBD
Admin page
13 | Round System Dashboard | 1. Separate tab in this page will have Round system dashboard. 2.Admin can set duration for each round, invalidate other user session ,calculation etc.. |  | Not started
16 | Teams Page | Admin should View Teams and associated user information |  | Complete
17 | Challenge Page |  | No | Not started

## Sheet3
Page No | UI Screens | Info | Specification? | Status
1 | Login Page | User Authentication and Authorization | Yes | Complete
2 | Default Page(after login) | A default page with following layout 1.Header Side Bar 2.Navbar 3.Mini Dashboard 4.SideBar 5.Centr Content ( A place holder for other page) | Yes | Complete
Header Side Bar
3 | Settings Page | 1.Opens desktop window to select an image to upload 2. Change Slogan 3.Change password | Yes | Complete
4 | Ranking Page | View Ranking content 1.Overall Ranking 2.Country level Ranking | Yes | Complete
5 | Activities Page | Manage User activities by adimin user | No | Not started
NavBar
|  | 1.Language Selection | Yes | Complete
|  | 2.Activity list with icon notification on outstanding activities | No | Not started
|  | 3.Logout | Yes | Complete
Side Bar
6 | Risk Page | To set the risk srategy at team level | Yes | Inprogress
7 | Dashboard Page | View Dashboard |  | Not started
8 | Company Page | 1. Projects 2. Departments 3. Financials | Yes | Inprogress
9 | Customer Portfolio Page | View Customer Info Search Customer Sorting Customer Filter Customer Upload Customer | No | Not started
10 | Market Page - Small Prospect Page | 1. Search Prospect 2. Filter Prospect 3. Make offer | No | Not started
11 | Market Page - Big Prospect Page | 1. Search Prospect 2. Filter Prospect 3. Make offer | Yes | Inprogress
| Market Page -Pop Up Window - Make Offer Page(Big prospect) | 1. View Selected Customer information 2. View Buyer Information 3. Enter Acceptence Rate 3. Enter Price info | Yes | Inprogress
12 | Oustanding offer | TBD
Admin page
13 | Round System Dashboard | 1. Separate tab in this page will have Round system dashboard. 2.Admin can set duration for each round, invalidate other user session ,calculation etc.. |  | Not started
16 | Teams Page | Admin should View Teams and associated user information |  | Complete
17 | Challenge Page |  | No | Not started